## Tabelle1
Sprint 1
Sprint 2
Sprint 3
Sprint 4
Sprint 5
Priority | Backlog Item | Task | Details (Wiki, URLs etc.) | Developers | Estimated Effort (1-10) | Effective Effort per Sprint
[6 empty] | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5
1 | Knowledge Crunching | Understanding what the game is about |  | ALL | 6 | 6
2 |  | Technology Analysis |  | ALL | 6 | 6
3 |  | Game Pattern Definition (MVC - GameLoop) |  | ALL | 3 | 3
4 | Choose a theme | Choose a theme to develop mechanics accordingly |  | ALL | 1 | 1
5 | Continuous Integration | Studying Typical Approaches |  | ALL | 3 | 3
6 |  | Implement CI workflow |  | ALL | 5 | 5
7 | Model Game Entities | Turret's Properties |  | Penazzi | 7 | 4 |  | 3
|  | Bullet's Properties |  | Penazzi, Foschini | 6 | 4 |  |  | 2
8 |  | Enemy's Properties |  | Foschini | 4 | 1 | 1 | 2
9 | Game Loop | Create initial GameLoop Actor |  | Parrinello | 6 |  | 6
9 |  | Figure out how many behaviors should have GameLoop |  | Parrinello | 1 |  | 1
10 | First Turret's Actor | Fire Logic |  | Penazzi | 5 |  | 5
|  | Bullet Spawning |  | Penazzi | 2 |  | 2
|  | Enemy's Actor |  | Foschini | 6 |  | 2 | 4
11 | ScalaFX VS LibGDX (yet another technology analysis) | Hello world with both tech |  | Alpi | 4 |  | 4
12 |  | Studying LibGDX documentation |  | Alpi | 2 |  | 2
13 | Architecture refactor | Which messages Actors should have |  | ALL | 5 |  | 5
|  | Collision: how they should be |  | ALL | 6 |  | 6
|  | Define Update and Start Phase |  | ALL | 3 |  | 3
16 | Create initial Launcher and its Root Actor | Implements the Root's Actor behaviors |  | Parrinello | 2 |  | 2
17 | First WaveSupervisor | First Implementation of WaveSupervisor |  | Parrinello | 2 |  | 2
18 | Immutability of Entities | Introduce the immutability in entity's creation phase |  | Alpi | 5 |  | 5
19 | Standard Model Messages | Introduce a Standard for Model Messages |  | Penazzi, Parrinello | 3 |  | 3
20 | First View Actor | Implements an easy View Actor for the first release |  | Alpi | 3 |  | 3
21 | Collision Handling | Implements a meccanish for the collision between the entities |  | Parrinello | 4 |  |  | 4
22 | GameField Rendering | Render the whole game including the field sprites |  | ALL | 3 |  |  | 3
23 | Mana Modelling | Study how the Mana/Sun should increase |  | Parrinello | 1 |  |  | 1
|  | Implements the Mana/Sun Model |  | Parrinello | 4 |  |  | 4
|  | Implements the interaction with Mana Model and Controller |  | Parrinello | 2 |  |  | 2
24 | Wave Modelling | Implements the Model behind the Wave concept |  | Penazzi | 3 |  |  | 3
|  | How Wave interact with GameLoop |  | Penazzi | 1 |  |  | 1
25 | Whole Game Interface | Create the view interface for the match |  | Foschini | 6 |  |  | 6
26 | Entity State concept | Introduce a state concept in each entities |  | Alpi | 2 |  |  | 2
27 | Cells logic | Add cells logic to viewport |  | Alpi | 3 |  |  | 3
|  | Add click listeners to cards and cells to place turrets |  | Alpi | 3 |  |  | 3
28 | Reduce HW Request | Figure out why the system is so HW intense |  | Alpi | 1 |  |  | 1
29 | Make Prolog | Make Prolog Theory but without the integration |  | Parrinello, Penazzi | 8 |  |  |  | 6
30 | Make Troop Actor | Create Troop Actor |  | Foschini, Penazzi | 3 |  |  | 3
|  | Introduce the concept of Troop in the Entity Model |  | Foschini, Penazzi | 3 |  |  | 3
31 | New troop entity types | Introduce new types of troop |  | Foschini, Penazzi | 2 |  |  |  | 2
32 | End match view | Render the end match view |  | Parrinello | 6 |  |  |  | 4
|  | Add statistics |  | Parrinello | 3
33 | Start match view | Render the start match view |  | Foschini | 2 |  |  |  | 2
|  | Add button for start the match |  | Foschini | 2 |  |  |  | 2
34 | In-game buttons | Add pause button |  | Alpi, Foschini | 2 |  |  |  |  | 5
|  | Add resume button |  | Alpi, Foschini | 2 |  |  |  |  | 4
|  | Add change game velocity button |  | Alpi, Foschini | 2 |  |  |  |  | 4
35 | Graphics Polish | Correct the position bullet height |  | Alpi | 2 |  |  |  |  | 3
|  | Increase assets quality |  | Alpi | 1 |  |  |  | 1
|  | Refactor of turrets placement position |  | Alpi | 2 |  |  |  | 1
37 | Integration Prolog | Prolog-Scala Integration in order to create random wave |  | Parrinello, Penazzi | 4 |  |  |  |  | 4
38 | Docs review | Reviews all documentations and correct little things |  | All | 3 |  |  |  |  | 6
39 | Fix bugs | Fix little bug around the whole game |  | Alpi, Parrinello | 4 |  |  |  |  | 5
40 | Increase usability | Increase usability introducing new buttons, align the text, ecc. |  | Alpi, Foschini | 4 |  |  |  |  | 4
|  | Add fade animation |  | Alpi | 4 |  |  |  |  | 4